## Sheet1
| jour | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
| Sommaire effort restant | 49 | 46 | 37 | 33 | 20 | 14 | 8 | 8 | 8 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Sommaire efforts dépensé | 3 | 9 | 4 | 13 | 6 | 6 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint 1. Créer la base de données et permettre aux utilisateurs de s'identifier
Numéro cas d'utilisation |  | jours du sprint / (effort restant estimé en début de journée ¦ heures travaillées ce jour)
| Cas d'utilisation ou user-story/tâche | 0 | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19 |  | 20 |  | 21 |  | 22
|  | 49 | 49 | 3 | 46 | 9 | 37 | 4 | 33 | 13 | 20 | 6 | 14 | 6 | 8 | 0 | 8 | 0 | 8 | 3 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5
1 | Créer Base de donnée
| Créer une base de donnée MySQL | 1 | 1 | 1 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Créer les tables et effectuer des test d'accès | 2 | 2 | 2 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Créer la classe permettant la manipulation de la BD | 12 | 12 | 0 | 12 | 5 | 7 | 4 | 3 | 3 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
2 | Se céer un compte
| Créer interface visuelle web permettant la connexion | 8 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 5 | 3 | 2 | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
| Créer la classe utilisateur | 4 | 4 | 0 | 4 | 4 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Vérifier les informations du formulaire et les stocker | 9 | 9 | 0 | 9 | 0 | 9 | 0 | 9 | 3 | 6 | 3 | 3 |  | 3 |  | 3 |  | 3 |  | 3 |  | 3 |  | 3 |  | 3 |  | 3 |  | 3 |  | 3 |  | 3 |  | 3 |  | 3 |  | 3 |  | 3 |  | 3
3 | Se connecter à son compte
| Créer l'interface de connexion | 5 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 2 | 3 | 1 | 2 | 4 | -2 |  | -2 |  | -2 |  | -2 |  | -2 |  | -2 |  | -2 |  | -2 |  | -2 |  | -2 |  | -2 |  | -2 |  | -2 |  | -2 |  | -2 |  | -2
| Vérifier les informations du formulaire | 3 | 3 | 0 | 3 | 0 | 3 | 0 | 3 |  | 3 |  | 3 | 2 | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
4 | Modifier les informations de son compte
| Créer l'interface d'accès au informations du compte | 3 | 3 | 0 | 3 | 0 | 3 | 0 | 3 |  | 3 |  | 3 |  | 3 |  | 3 |  | 3 | 2 | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
| Vérifier les informations du formulaire et les stocker | 2 | 2 | 0 | 2 | 0 | 2 | 0 | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 | 1 | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
État du sprint backlog après jour 3 (fin du jour 3, début du jour 4)
traduit de http://agilesoftwaredevelopment.com/scrum/simple-sprint-backlog fait par Artem Marchenko
basé sur: | http://agilesoftwaredevelopment.com/scrum/simple-sprint-backlog
Note on C6: sprint goal
Note on D10: Estimation initiale
Note on E10: Pour chaque jour, la première colonne indique le temps restant, et la deuxième colonne indique le temps travaillé sur cette tâche ce jour là. Normalement, la première colonne du jour J est égal à la différence entre la première colonne du jour J-1 (estimation en temps restant, en date du jour J-1) et de l'effort passé sur la tâche le jour J-1. Sauf si on s'est trompé d'estomation au jour J-1, auquel cas la première colonne du jour J est plus grande (on a sous-estimé) ou plus petite (on a surestimé) l'effort requis par la tâche
Note on U10: Effort left went up after some new work has been discovered
Note on B11: Id of the story. To simplify linking to the product backlog
Note on C11: User story being implemented. See http://agilesoftwaredevelopment.com/scrum/simple-product-backlog
Note on C13: Task description are written in the language that team likes. It does not have to be management understandable or "correct". In this case the accurate description would be something like "Implement reading the provider's data directory on the server side", however, team decide to make it just "Read provider's data directory", because it was simpler and everybody on the team perfectly understood what this task was about
Note on D14: The team tries not have tasks bigger, than 16 ideal engineering hours. If they happen to have a bigger task, they try to split it into two smaller and more managable ones
Note on E14: The team tries not have tasks bigger, than 16 ideal engineering hours. If they happen to have a bigger task, they try to split it into two smaller and more managable ones
Note on C45: See for reference and comments. Feel free to remove the link, though it would be very kind of you to leave it somewhere on the sheet